## Description
"Project name" Acceptance Sheet Document
The Acceptance Sheet contains information about all tests and their results.
An acceptance sheet should be sent as an attach to PM, TM and PC after the MAT, the New Features Testing (if an acceptance test will not be executed) and the Acceptance Test.
A common description of the quality of the build in accordance with last testing type should be included in such letters.
Build Info & Testing tabs description
Build Information
Build Number | The number of the build that was tested.
Test type | Smoke Test | A subset of all defined/planned test cases that cover the main functionality of a component or system, to ascertaining that the most crucial functions of a program work, but not bothering with finer details.
| MAT | Minimal Acceptance Test: A test directed to check that all application functions can be performed with correct data. Check if all application features can be used under correct conditions. For complex and large applications, a limited set of functions and scenarios is used.
| AT | Full Acceptance Test: A test directed to verify that the software can be used by end users to perform the functions and tasks for which the software was built under any conditions. Business logic + functionality + form behaviour + GUI test + Usability test + localisation test (if applicable) — a complete test of the functionality and interface under any conditions (positive and negative testing). All these tests make up a maximal set for testing, but it can also comprise one or several parts (depending on the end-users aims while using the product).
| NFT | Full Acceptance Test of New Features: A test directed to verify if the feature is completely and correctly implemented and if the logic of the product is not affected. Check if all application features can be used under correct conditions. For complex and large applications, a limited set of functions and scenarios is used.
| DV | Defects Validation: A test directed to check all the defects that were resolved against the current build. Testing of the feature that contained the fixed defect.
| Regression Test | Testing of a previously tested program following modification to ensure that defects have not been introduced or uncovered in unchanged areas of the software, as a result of the changes made. It is performed when the software or its environment is changed.
| Crossbrowser Test | Testing of the program to determine if it's functional on different internet browsers.
Add test type if it's not on the list.
Add test type if it's not on the list.
Test date | Date range when the tests were performed.
Tester | Testers who performed tests.
Environment / OS | Environment / OS on which the tests were performed.
Browser | Browser on which the tests were performed.
Project Size | Subjective metric set for the first build by QA Manager for further tracking of quality.
Quality | Subjective quality rate of the build.
Quality rate | Calculated quality rate of the build.
Total defects quantity | Quantity of all active defects in Jira by the end of testing.
New defects quantity | Quantity of active defects in Jira by the end of testing found in the current build.
Comments | Any comments that are needed.
New defects found
New defects quantity | Quantity of active defects by the end of testing found in the current build.
With high severity | Quantity of active defects with high severity (Average, Major, Critical) by the end of testing found in the current build.
Comments | Any comments that are needed.
Jira defects status report
Open | Quantity of defects having "Open" state by the end of testing (the issue is open and ready for the assignee to start work on it).
In Progress | Quantity of defects having "In Progress" state by the end of testing (this issue is being actively worked on at the moment by the assignee).
Resolved | Quantity of defects having "Resolved" state by the end of testing (A resolution has been taken, and it is awaiting verification by reporter. From here issues are either reopened, or are closed).
Postponed | Quantity of defects having "Postponed" state by the end of testing.
To be reformulated | Quantity of defects having "To be reformulated" state by the end of testing.
Total | Total quantity of active defects in JIRA.
Comments | Any comments that are needed.
Defect validation report
Number of checked defects | Quantity of defects checked in the current build.
Reject: Critical | Quantity of rejected defects with "Critical" severity in the current build.
Reject: Major | Quantity of rejected defects with "Major" severity in the current build.
Reject: Average | Quantity of rejected defects with "Average" severity in the current build.
Reject: Minor | Quantity of rejected defects with "Minor" severity in the current build.
Reject: Enhancement | Quantity of rejected defects with "Enhancementl" severity in the current build.
Not checked | Quantity of defects required to be checked but not checked.
Percent of Rejects | Percentage of rejected defects.
Comments | Any comments that are needed.
CR validation report
Number of checked CRs | Quantity of CRs checked in the current build.
Rejected | Quantity of rejected CRs in the current build.
Not checked | Quantity of CRs required to be checked but not checked.
Percent of Rejects | Percentage of rejected CRs.
Comments | Any comments that are needed.
Jira defects severity report
Critical | Quantity of active defects with "Critical" severity by the end of testing.
Major | Quantity of active defects with "Major" severity by the end of testing.
Average | Quantity of active defects with "Average" severity by the end of testing.
Minor | Quantity of active defects with "Minor" severity by the end of testing.
Enhancement | Quantity of active defects with "Enhancement" severity by the end of testing.
Total | Total quantity of active defects in JIRA.
Comments | Any comments that are needed.
Results used by the tester when filling cells of the Acceptance Sheet
OK | Everything works fine.
Partially tested | Function was tested partially due to some reasons.
Enhancement | Design, navigation, functional proposals and advice. This Defect is not obligatory to be fixed.
Minor | Design error. Functional error that rarely occurs.
Average | Functional error which is not very important. Function behaviour does not correspond to the Use Case completely (for example fields max length, etc). This defect does not influence greatly on the user’s work.
Major | Functional error which disturbs normal work of an application, but the error does not block the work of this part of application completely.
Critical | Functional error which blocks completely some part of functional or all application.
Not available | Function is not available for test.
Not implemented | Function has been not implemented yet.
Not tested | Function has not been tested.
Build quality range
High | Applies to MAT, AT, NFT, Regression test, Crossbrowser test. A few enhancement/minor GUI problems exist in the application, the application works as designed, and conforms the end-user’s requirements.
Above Medium | Applies to MAT, AT, NFT, Regression test, Crossbrowser test. Some minor issues exist in the application. It works as designed and these defects do not affect seriously end-user’s work. Insignificant functional or GUI issues exist, fixing of which would slightly improve a use case behavior or performance. The use cases complete as designed.
Medium | Applies to MAT, AT, NFT, Regression test, Crossbrowser test. A quantity of minor and a few major problems disrupting the normal user’s work. There are issues which affects functional areas within minor features. The use cases can be completed with a minimum of workaround.
Below Medium | Applies to MAT, AT, NFT, Regression test, Crossbrowser test. A great deal of minor and major problems disrupting the normal user’s work. There are issues which affects functional areas within major features. The use cases can be completed with a minimum of workaround.
Low | Applies to MAT, AT, NFT, Regression test, Crossbrowser test. Critical or major issues exist. The user can not work properly with the application. There are issues which affect the use of one or more major features within the application. There may be a workaround, however, and testing can continue.
Acceptable | Applies to ST and means that the build is acceptable for further testing. Applies to DV and means that 10% or less of issues rejected.
Not Acceptable | Applies to ST and means that the build is not acceptable for further testing. The test team is blocked. Applies to DV and means that more than 10% of issues rejected.
Testing Plan tab description
Information about required browsers and OS, necessary tests and their date and results.
Note on B17: It is recommended not to merge columns with different test types.
Note on B18: It is recommended not to merge columns with different test types.
Note on A91: Required
Note on A93: Required
Note on A95: Required
Note on A96: Required
Note on A97: Required

## Build Info
Build Information | [5 empty] | Required
Build number | 1 | 1 | 2 | 2 | 2 | 3
Test type | Smoke Test | AT | Smoke Test | DV | Regression Test | 3
Test date | 2012-10-31 | 11-12.06.2012 | 2012-10-31 | 2012-10-09 | 2012-11-01 | 3
Tester | O. Kot | O. Kot | O. Kot | O. Kot | O. Kot | 3
Environment / OS | Win 7 | Win 7 | Win 7 | Win 7 | Win 7
Browser | IE 9 | IE 9 | IE 9 | IE 9 | IE 9
Project size | 100 | 100 | 100 | 100 | 100
Quality | Acceptable | Low | Acceptable | Medium | Below Medium | 3
Quality rate | 1 | 0.068 | 0.068 | 0.527 | 0.375 | 3
Total defects quantity | 0 | 52 | 52 | 22 | 32 | 3
New defects quantity | 0 | 52 | 0 | 0 | 10
Comments
Statistics for Defects
New defects found:
New defects quantity | 0 | 52 | 0 | 0 | 10
With high severity | 0 | 8 | 0 | 0 | 0
Comments
Jira defects status report: | [5 empty] | 3
Open | 0 | 52 | 17 | 17 | 27
In Progress | 0 | 0 | 5 | 5 | 5
Resolved | 0 | 0 | 30 | 0 | 0
Postponed | 0 | 0 | 0 | 0 | 0
To be reformulated | 0 | 0 | 0 | 0 | 0
Total | 0 | 52 | 52 | 22 | 32
Comments
Defect validation report: | [5 empty] | 3
Number of checked defects | – | – | – | 30 | –
Reject: Critical | – | – | – | 0 | –
Reject: Major | – | – | – | 0 | –
Reject: Average | – | – | – | 1 | –
Reject: Minor | – | – | – | 3 | –
Reject: Enhancement | – | – | – | 0 | –
Not checked | – | – | – | 1 | –
Percent of Rejects |  |  |  | 16.13%
Comments
CR validation report:
Number of checked CRs | – | – | – | – | –
Rejected | – | – | – | – | –
Not checked | – | – | – | – | –
Percent of Rejects | – | – | – | – | –
Comments
Jira defects severity report: | [5 empty] | 3
Critical | 0 | 1 | 1 | 0 | 0
Major | 0 | 2 | 2 | 0 | 0
Average | 0 | 18 | 18 | 10 | 17
Minor | 0 | 26 | 26 | 12 | 15
Enhancement | 0 | 5 | 5 | 0 | 0
Total | 0 | 52 | 52 | 22 | 32
Comments
3
3

## Front End
Build |  |  | 1.0
Test type |  |  | AT
Test date |  |  | 09.12.22-14.12.22
Tester |  |  | Anna Plotnikova
Project Environment |  |  | https://photostudio.demohoster.com
Operating System |  |  | Win 10 х64
Browser |  |  | Google Chrome - 108.0.5359.98
Project Information |  |  | Test Cases Statistics
Project name | Gregory Olsen. Photo Studio. |  | Status | Quantity | Percentage (%)
Project URL | https://photostudio.demohoster.com/ |  | OK | 157 | 56.88%
Database |  |  | Partially tested | 0 | 0%
Default browser | Google Chrome 108.0.5359.98 |  | Enhancement | 1 | 0.3623%
|  |  | Minor | 44 | 15.94%
|  |  | Average | 26 | 9.42%
|  |  | Major | 9 | 3.261%
|  |  | Critical | 3 | 1.087%
|  |  | Not available | 36 | 13.04%
|  |  | Not implemented | 0 | 0%
|  |  | Not tested | 0 | 0%
|  |  | Total cases | 276
Module | Test type | Function | Result | Issues | Comments
Header
Logo
| AT | GUI | Minor | QATC-724969
| AT | General | OK
Search string
| AT | GUI | Minor | QATC-725117
| AT | General | Major | QATC-725111 | Upd: average - major
Tabs
| AT | GUI | Average | QATC-724982 | Minor
QATC-725060
|  |  |  | QATC-724994 | Minor
| AT | General | Major | QATC-725038
|  |  |  | QATC-725048 | Average
General
Favicon
| AT | GUI | Minor | QATC-724988
| AT | General | OK
Footer
Email link
| AT | GUI | OK
| AT | General | Average | QATC-725292
Facebook link
| AT | GUI | OK
| AT | General | OK
| AT | Twitter link
| AT | GUI | OK
| AT | General | OK
Instagram link
| AT | GUI | OK
| AT | General | OK
YouTube link
| AT | GUI | OK
| AT | General | OK
Presence on all pages
| AT | GUI | Average | QATC-726212
| AT | General | OK
HOME
Preview photos
| AT | GUI | OK
| AT | General | OK
Links to corresponding galleries
| AT | GUI | OK
| AT | General | Average | QATC-725169
Question-answer zone
| AT | GUI | OK
| AT | General | OK
WORK.Portrait
Page title
| AT | GUI | OK
| AT | General | OK
Thumbnails
| AT | GUI | Minor | QATC-725338
| AT | General | Average | QATC-725342
Preview photos
| AT | GUI | Minor | QATC-725306
| AT | General | OK
Photo viewer
| AT | GUI | Average | QATC-725310
| AT | General | Enhancement | QATC-725315
Pagination
| AT | GUI | OK
| AT | General | Average | QATC-725331
Photo order
| AT | GUI | Minor | QATC-725338
| AT | General | OK
WORK.Lifestyle
Page title
| AT | GUI | OK
| AT | General | OK
Thumbnails
| AT | GUI | Average | QATC-725377
| AT | General | OK
Preview photos
| AT | GUI | OK
| AT | General | OK
Photo viewer
| AT | GUI | Average | QATC-725384
| AT | General | Average | QATC-725352
Pagination
| AT | GUI | OK
| AT | General | OK
Photo order
| AT | GUI | OK
| AT | General | OK
WORK.Travel
Page title
| AT | GUI | OK
| AT | General | OK
Thumbnails
| AT | GUI | OK
| AT | General | OK
Preview photos
| AT | GUI | OK
| AT | General | OK
Photo viewer
| AT | GUI | Average | QATC-725391
| AT | General | OK
Pagination
| AT | GUI | OK
| AT | General | OK
Photo order
| AT | GUI | OK
| AT | General | OK
WORK.Motion
Page title
| AT | GUI | Critical | QATC-725038
| AT | General | Not available
Thumbnails
| AT | GUI | Not available
| AT | General | Not available
Preview photos
| AT | GUI | Not available
| AT | General | Not available
Photo viewer
| AT | GUI | Not available
| AT | General | Not available
Pagination
| AT | GUI | Not available
| AT | General | Not available
Photo order
| AT | GUI | Not available
| AT | General | Not available
CONNECT.Page Bio & Press
Page title
| AT | GUI | OK
| AT | General | OK
Greg’s photo
| AT | GUI | Major | QATC-725412
| AT | General | Not available
Text
| AT | GUI | Major | QATC-725425
| AT | General | Not available
CONNECT.Clients
Page title
| AT | GUI | Minor | QATC-725431
| AT | General | OK
List of Pictures
| AT | GUI | Major | QATC-725837
|  |  |  | QATC-725855 | Minor
|  |  |  | QATC-725863 | Average
| AT | General | OK
Links in pictures
| AT | GUI | OK
| AT | General | Major | QATC-725883 | Minor
|  |  |  | QATC-725890 | upd: major - average
QATC-725896
|  |  |  | QATC-725902 | Minor
|  |  |  | QATC-725908 | Average
CONNECT.Philanthropy
Page title
| AT | GUI | OK
| AT | General | OK
Photo
| AT | GUI | OK
| AT | General | OK
Greg’s article
| AT | GUI | Average | QATC-725927 | Minor
QATC-725938
| AT | General | OK
CONNECT.Contact
Page title
| AT | GUI | OK
| AT | General | OK
Greg’s photo
| AT | GUI | OK
| AT | General | OK
Message for customers
| AT | GUI | OK
| AT | General | OK
SEND AN EMAIL form
| AT | GUI | Minor | QATC-726059
| AT | General | Critical | QATC-726103
Feedback form. Firstname
| AT | GUI | Average | QATC-726079
| AT | General | Major | QATC-726095
Feedback form. Lastname
| AT | GUI | Average | QATC-726071 | Average
QATC-726119
| AT | General | Not available
Feedback form. Email
| AT | GUI | Average | QATC-726071
| AT | General | Not available
Feedback form. Subject
| AT | GUI | Average | QATC-726071
| AT | General | Not available
Feedback form. Message
| AT | GUI | Average | QATC-726071
| AT | General | Not available
Send button
| AT | GUI | OK
| AT | General | Not available
SESSIONS. Our Sessions
Page title
| AT | GUI | OK
| AT | General | OK
List of sessions
| AT | GUI | Minor | QATC-726193
| AT | General | OK
Describing (Mini Studio Session)
| AT | GUI | OK
| AT | General | OK
Describing (Mini Outdoor Session)
| AT | GUI | OK
| AT | General | OK
| AT | Describing (Standard Session)
| AT | GUI | OK
| AT | General | OK
Book Session. General
Page title
| AT | GUI | OK
| AT | General | OK
Back button
| AT | GUI | Minor
| AT | General | OK
Book Session. Mini Studio Session
Picture
| AT | GUI | OK
| AT | General | OK
Start price
| AT | GUI | OK
| AT | General | OK
Additional subjects dropdown
| AT | GUI | Average | QATC-726210
| AT | General | OK
Button Book
| AT | GUI | OK
| AT | General | OK
Details
| AT | GUI | OK
| AT | General | OK
Book Session. Mini Outdoor Session
Picture
| AT | GUI | OK
| AT | General | OK
| AT | Start price
| AT | GUI | OK
| AT | General | OK
Additional subjects dropdown
| AT | GUI | OK
| AT | General | OK
Button Book
| AT | GUI | OK
| AT | General | OK
Details
| AT | GUI | OK
| AT | General | OK
Book Session. Standard Session
Picture
| AT | GUI | OK
| AT | General | OK
Start price
| AT | GUI | Minor | QATC-726218
| AT | General | OK
Additional subjects dropdown
| AT | GUI | Average | QATC-726215
| AT | General | OK
Button Book
| AT | GUI | OK
| AT | General | OK
Details
| AT | GUI | OK
| AT | General | OK
Book Information. Mini Studio session
Session information. Photo
| AT | GUI | OK
| AT | General | OK
Session information. Session name
| AT | GUI | OK
| AT | General | OK
Session information. Additional Subjects
| AT | GUI | OK
| AT | General | OK
Session information. Total Price
| AT | GUI | OK
| AT | General | Major | QATC-726222
Contact information. Email
| AT | GUI | Minor | QATC-726261
QATC-726279
| AT | General | OK
Contact information. Checkbox "Keep me up to date on news"
| AT | GUI | Minor | QATC-726266
|  |  |  | QATC-726267 | Enhancement
| AT | General | OK
Contact information. Firstname
| AT | GUI | Minor | QATC-726279
| AT | General | OK
Contact information. Lastname
| AT | GUI | Minor | QATC-726279
| AT | General | OK
Contact information. Company
| AT | GUI | Average | QATC-726278
| AT | General | OK
Contact information. Address
| AT | GUI | Minor | QATC-726279
| AT | General | OK
Contact information. Apartment
| AT | GUI | Minor | QATC-726279
| AT | General | OK
Contact information. City
| AT | GUI | Minor | QATC-726279
| AT | General | OK
Contact information. Country
| AT | GUI | Minor | QATC-726279
| AT | General | OK
Contact information. Postal code
| AT | GUI | Minor | QATC-726279
| AT | General | OK
Contact information. Phone
| AT | GUI | Minor | QATC-726261
QATC-726279
| AT | General | OK
Contact information. Checkbox "Save this information for next time"
| AT | GUI | Average | QATC-726267 | Enhancement
QATC-726273
| AT | General | Not available
Button "Continue to payment method"
| AT | GUI | OK
| AT | General | OK
SESSIONS.Book Information. Mini Outdoor session
Session information. Photo
| AT | GUI | Minor | QATC-726226
| AT | General | OK
Session information. Session name
| AT | GUI | OK
| AT | General | OK
Session information. Additional Subjects
| AT | GUI | OK
| AT | General | OK
Session information. Total Price
| AT | GUI | OK
| AT | General | OK
Contact information. Email
| AT | GUI | Minor | QATC-726261
QATC-726279
| AT | General | OK
Contact information. Checkbox "Keep me up to date on news"
| AT | GUI | Minor | QATC-726266
|  |  |  | QATC-726267 | Enhancement
| AT | General | OK
Contact information. Firstname
| AT | GUI | Minor | QATC-726279
| AT | General | OK
Contact information. Lastname
| AT | GUI | Minor | QATC-726279
| AT | General | OK
Contact information. Company
| AT | GUI | Average | QATC-726278
| AT | General | OK
Contact information. Address
| AT | GUI | Minor | QATC-726279
| AT | General | OK
Contact information. Apartment
| AT | GUI | Minor | QATC-726279
| AT | General | OK
Contact information. City
| AT | GUI | Minor | QATC-726279
| AT | General | OK
Contact information. Country
| AT | GUI | Minor | QATC-726279
| AT | General | OK
Contact information. Postal code
| AT | GUI | Minor | QATC-726279
| AT | General | OK
Contact information. Phone
| AT | GUI | Minor | QATC-726279
| AT | General | OK
Contact information. Checkbox "Save this information for next time"
| AT | GUI | Average | QATC-726267 | Enhancement
QATC-726273
| AT | General | Not available
Button "Continue to payment method"
| AT | GUI | OK
| AT | General | OK
Book Information. Standard session
Session information. Photo
| AT | GUI | Minor | QATC-726230
| AT | General | OK
Session information. Session name
| AT | GUI | OK
| AT | General | OK
Session information. Additional Subjects
| AT | GUI | OK
| AT | General | OK
Session information. Total Price
| AT | GUI | OK
| AT | General | Major | QATC-726233
Contact information. Email
| AT | GUI | Minor | QATC-726261
QATC-726279
| AT | General | OK
Contact information. Checkbox "Keep me up to date on news"
| AT | GUI | Minor | QATC-726266
|  |  |  | QATC-726267 | Enhancement
| AT | General | OK
Contact information. Firstname
| AT | GUI | Minor | QATC-726279
| AT | General | OK
Contact information. Lastname
| AT | GUI | Minor | QATC-726279
| AT | General | OK
Contact information. Company
| AT | GUI | Average | QATC-726278
| AT | General | OK
Contact information. Address
| AT | GUI | Minor | QATC-726279
| AT | General | OK
Contact information. Apartment
| AT | GUI | Minor | QATC-726279
| AT | General | OK
Contact information. City
| AT | GUI | Minor | QATC-726279
| AT | General | OK
Contact information. Country
| AT | GUI | Minor | QATC-726279
| AT | General | OK
Contact information. Postal code
| AT | GUI | Minor | QATC-726279
| AT | General | OK
Contact information. Phone
| AT | GUI | Minor | QATC-726279
| AT | General | OK
Contact information. Checkbox "Save this information for next time"
| AT | GUI | Average | QATC-726267 | Enhancement
QATC-726273
| AT | General | Not available
Button "Continue to payment method"
| AT | GUI | Minor | QATC-726275
| AT | General | OK
Payment
Payment form. Heading
| AT | GUI | Critical | QATC-726285
| AT | General | Not available
Payment form. Owner
| AT | GUI | Not available
| AT | General | Not available
Payment form. CVV
| AT | GUI | Not available
| AT | General | Not available
Payment form. Card number
| AT | GUI | Not available
| AT | General | Not available
Payment form. Expiration date. Date picker Month
| AT | GUI | Not available
| AT | General | Not available
Payment form. Expiration date. Date picker Year
| AT | GUI | Not available
| AT | General | Not available
Pictures Payment systems
| AT | GUI | Not available
| AT | General | Not available
Button Confirm
| AT | GUI | Not available
| AT | General | Not available
INSTAOLSEN
Link of Instagram
| AT | GUI | OK
| AT | General | Average | QATC-725130
Note on A1: Required
Note on A2: Required
Note on A3: Required
Note on A4: Required
Note on A5: Required
Note on A21: Required
Note on C21: Required
Note on D21: Required

## Testing Plan
Requirement | Software | Comments |  |  |  | Test Team | Project Environment | URL
Environment / Operating System | Win 7 |  |  |  |  | O. Kot | Live | http://projectx_live.com
| MacOS 10.7.2 |  |  | 6.8 % |  |  | UAT | http://projectx_uat.com
| iPad 3 | [5 empty] | Test | http://projectx_test.com
| iPhone 5 | [5 empty] | Dev | http://projectx_dev.com
iPhone 4S
Android 4.0
Android 2.3
Add environment / operating system if it's not on the list.
Add environment / operating system if it's not on the list.
Browser | — | Used for testing environment with built-in browser (e.g. in Android system).
IE 10
| IE 11 |  |  | 6.8 %
IE 8
Firefox 17
Chrome 23
Safari 6
Safari 5
Opera 12
Add browser if it's not on the list.
Add browser if it's not on the list.
Language: English
Main Test Condition
OS | Win 7
Browser | IE 9
Additional Test Plan
OS | Browser | Build Number | Test Type | Test date | Quality
Android 4.0 | — | 1.5.2 | Crossbrowser Test | 04 - 05.12.2012 | Low
Win 7 | Safari 5 | 1.5.2 | Crossbrowser Test | 04 - 05.12.2012 | Medium
iPhone 5 | Safari 6 | 1.5.2 | Crossbrowser Test | 04 - 05.12.2012 | High
MacOS 10.7.2 | Safari 5 | 1.5.2 | Crossbrowser Test | 2012-12-06 | Low